## QA Status
Application | Name | Jira ID | Status | QA action this week | Summary | Notes | Environment | Type
Fulfillment Console | Akilandeswari Sundararajan | BSD-27316 | Complete | Verified in PROD | [Backend] - Fulfillment - correct status for metadataDelivery and metadataOnly Delivery orders and fix metadata content for them |  | PROD | Story
Fulfillment Console | Akilandeswari Sundararajan | BSD-29582 | Complete | Verified in PROD | [Frontend] Add a refresh button on the table header |  | PROD | Story
Fulfillment Console | Akilandeswari Sundararajan | BSD-29587 | In Progress (DEV) | Sent to dev | OC-FF-QA : Bulk selection Apply button disabled when selecting any jobs and any status | QA sent back to dev during week | PROD | Bug
Fulfillment Console | Shubham Zurang | BSD-29685 | Complete | Sent to dev | Concurrent Assignment Allows Multiple Successful Responses for the Same Order Instead of Showing "Already Assigned" Message | QA sent back to dev during week | UAT | Bug
Fulfillment Console | Babloo Kumar | BSD-29791 | Complete | Verified & closed | [Frontend] - Fulfillment - Bind tarSize in package details panel |  | Dev | Story
Fulfillment Console | Akilandeswari Sundararajan | BSD-29844 | Complete | Verified & closed | OC-FF-QA : Some user name is not available in Assign To dropdown list |  | Dev | Bug
Fulfillment Console | Akilandeswari Sundararajan | BSD-29870 | Complete | Sent to dev | OC-FF-QA : DSID is blank in Order table for MetadataOnlyDelivery orders (Specific partner) | QA sent back to dev during week | PROD | Bug
Fulfillment Console | Babloo Kumar | BSD-29883 | In Progress (DEV) | Sent to dev | OC-FF-QA : Line items and Orders grid data load exceeds 30 seconds on fast scroll with 1 year date range | QA sent back to dev during week | PROD | Bug
Fulfillment Console | Babloo Kumar | BSD-29886 | Complete | Verified & closed | OC-FF-QA : Edit Metadata editor inserts two lines instead of one on Enter key press |  | Dev | Bug
Fulfillment Console | Babloo Kumar | BSD-29887 | Complete | Verified & closed | OC-FF-QA : Downloaded metadata file is invalid XML after update and save |  | Dev | Bug
MSC Fulfillment Performance Metrics | Babloo Kumar | BSD-27950 | Complete | Verified & closed | FFP-QA: UI incorrectly showing “SLA Launch – Broke Partner SLA: No” when it should be Yes |  | Dev | Bug
MSC Fulfillment Performance Metrics | Akilandeswari Sundararajan | BSD-29823 | Complete | Verified & closed | MFP-FE: Add metrics universe group dropdown to dashboard filter bar |  | Dev | Story
MSC Fulfillment Performance Metrics | Akilandeswari Sundararajan | BSD-29911 | To Do | Newly created | OC-FP-QA : View Exclusion shows always 1000 count when Global Group option is selected |  | Dev | Bug
Admin Console | Shubham Zurang | BSD-29862 | Complete | Verified & closed | Read Only user receives Access Denied message instead of being granted read-only access to Admin Console |  | Dev | Bug
Admin Console | Shubham Zurang | BSD-29869 | Complete | Verified & closed | Request Access button is not displayed for user with No Access on Admin Console access denied page |  | Dev | Bug
Admin Console | Babloo Kumar | BSD-29900 | To Do | Newly created | OC-AC-QA: Requests to Manage section is visible for Read-only user on Users and Permissions page |  | UAT | Bug
Admin Console | Babloo Kumar | BSD-29937 | To Do | Newly created | OC-AC-QA: Dark theme - "+" icon color should be black and counter design/background color mismatch in CSP Applies until controls |  | PROD | Bug
Admin Console | Babloo Kumar | BSD-29939 | To Do | Newly created | OC-AC-QA: Blocker icon cursor briefly displayed when clicking Update policy on CSP Policy Form |  | PROD | Bug
AI Chatbot | Akilandeswari Sundararajan | ADX-4977 | Done | Verified & closed | AI-OC-QA : AI Chatbot is not giving response |  | Dev | Bug
AI Chatbot | Babloo Kumar | ADX-5054 | Done | Verified & closed | V2-AI-QA- Chatbox remains disabled after session closure in Agent Chatbot but correctly enabled in AI Chatbot |  | Dev | Bug
Partner Console | Alekya Byneni | BSD-28523 | Complete | Verified & closed | PC -ADMIN - UI [PCA-04][Story] Tree navigation - dynamic leaf selection |  | Dev | Story
Partner Console | Sheetal Aware | BSD-28532 | Complete | Verified & closed | PC -ADMIN - UI [PCA-13][Story] Mapping Tables editor |  | Dev | Story
Partner Console | Rucha Pawar | BSD-28606 | In Analysis | Reopened | OC-PC-QA: Notifications can't be saved as dropdown field isn't retaining values | QA reopened during week | UAT | Bug
Partner Console | Anjan Dutta | BSD-28919 | Complete | Verified in UAT | OC-PC-QA: In Draft count of material is not matching with data present. |  | UAT | Bug
Partner Console | Rucha Pawar | BSD-29043 | In Progress (DEV) | Verified in UAT | OC-PC-QA: Draft name is not showing |  | UAT | Bug
Partner Console | Rucha Pawar | BSD-29376 | In Progress (DEV) | Sent to dev | OC-PC-QA: Saved filters dropdown overlay blocks interaction with main directory content | QA sent back to dev during week | UAT | Bug
Partner Console | Anjan Dutta | BSD-29436 | Complete | Verified in UAT | OC-PC-QA: Materials count not updating after Save |  | UAT | Bug
Partner Console | Anjan Dutta | BSD-29701 | In Progress (DEV) | Sent to dev | User reported UI bugs | QA sent back to dev during week |  | Bug
Partner Console | Anjan Dutta | BSD-29908 | To Do | Newly created | OC-PC-QA: All Package Structure Selection in Audio TAB for individual audio material is not working |  | UAT | Bug
Partner Console | Alekya Byneni | BSD-29909 | To Do | Newly created | OC-PC-QA: White patches observed while adding new data |  | Dev | Bug
Partner Console | Alekya Byneni | BSD-29910 | To Do | Newly created | OC-PC-QA: Column Search functionality is not working |  | Dev | Bug
Partner Console | Alekya Byneni | BSD-29912 | To Do | Newly created | OC-PC-QA: Unable to duplicate newly created Auth Method |  | Dev | Bug
Partner Console | Rucha Pawar | BSD-29936 | In Progress (DEV) | Newly created | OC-PC-QA: Few blank values displaying in Package Structure dropdown filter |  | UAT | Bug
Partner Console | Alekya Byneni | BSD-29961 | To Do | Newly created | OC-PC-QA: Unable to create new Manage values -> Partner Settings -> Brand |  | Dev | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29355 | In Progress (DEV) | Sent to dev | OC-MIC-QA-Uploader Email when selected the columns are mis aligned | QA sent back to dev during week | UAT | Bug
Media Ingest Console | Rahul J | BSD-29358 | Complete | Verified in PROD | OC-MIC-QA-Record count for 'Select All' changes and mismatches total filter count after selection |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29387 | To Do | Sent to dev | OC-MIC-QA-Uploader Email column not updated/populated for Dub cards orders in MIC | QA sent back to dev during week | PROD | Bug
Media Ingest Console | Dhamodharan K | BSD-29440 | Complete | Verified in PROD | OC-MIC-QA-Filter "Title" category incorrectly displays Episode Numbers instead of Title suggestions |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29502 | Complete | Verified in PROD | OC-MIC-QA-Document details are not updated in MIC Console |  | PROD | Bug
Media Ingest Console | Rahul J | BSD-29531 | Complete | Verified in PROD | OC-MIC-QA-Internal Search: Filter selection does not persist and resets to default "Show All" state |  | PROD | Bug
Media Ingest Console | Kaustubh Vedpathak | BSD-29741 | Complete | Verified & closed | MIC - FE - Integrate total alert counts for the alerts |  | Dev | Story
Media Ingest Console | Rahul J | BSD-29743 | In Progress (DEV) | Sent to dev | OC-MIC-QA- History logs status in right detail panel mismatch with the main table status | QA sent back to dev during week | PROD | Bug
Media Ingest Console | Rahul J | BSD-29877 | Complete | Sent to dev | OC-MIC-QA- Copy Clipboard Icons Incorrectly Displayed in Language and Sub Type Columns | QA sent back to dev during week | UAT | Bug
Media Ingest Console | Rahul J | BSD-29879 | Complete | Verified & closed | OC-MIC-QA-Select all is not selecting all the task in flagged filter. only yes option count is selected |  | Dev | Bug
Media Ingest Console | Rahul J | BSD-29882 | Complete | Sent to dev | OC-MIC-QA-Filter count shows total records and previously selected values disappear from Active Filters after searching and selecting a new value | QA sent back to dev during week |  | Bug
Media Ingest Console | Rahul J | BSD-29941 | In Progress (QA) | Newly created | OC-MIC-QA: Selected Big Filter is duplicated 2x in the Active Filters section |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29959 | To Do | Newly created | OC-MIC-QA-Flagged Filtering is not working |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29960 | To Do | Newly created | OC-MIC-QA-Filtering took more than 20 seconds to load Data in UI |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29980 | To Do | Newly created | OC-MIC-QA-DSID is missing for few workorders |  | PROD | Bug
Media Ingest Console | Ravi Balasundaram | BSD-29981 | In Progress (DEV) | Newly created | OC-MIC-QA-Air Date filtering is failing in PROD |  | PROD | Bug
QC Workbench | Rahul J | BSD-28748 | Complete | Verified in PROD | QCWB - FE - Prioritization and cleanup of unnecessary calls on load and on idle |  | PROD | Story
QC Workbench | Rahul J | BSD-29753 | Complete | Verified in PROD | OC-QCWB-QA-Tooltip not showing for long titles in the Details panel |  | PROD | Bug
QC Workbench | Rahul J | BSD-29756 | Complete | Verified & closed | OC-QCWB-QA-Operator tab is not displaying all operator details in QCWB admin page |  | Dev | Bug
QC Workbench | Rahul J | BSD-29836 | Complete | Verified & closed | [Frontend] Implement Relaunch Initiation Failed event audit log |  | Dev | Story
QC Workbench | Shankhadeep Das | BSD-29842 | Complete | Verified & closed | [Backend] Task List Columns – Remove temporary Real Data column |  | Dev | Story
Library Manager | Bhawna Kaushik | BSD-28828 | Complete | Verified & closed | [LMv2 PROD] Filter Received At is present but column is not present for that filter |  | Dev | Bug
Library Manager | Bhawna Kaushik | BSD-29578 | Complete | Verified & closed | LM2.0 DEV: Value of column Received At is not correct in exported file |  | Dev | Bug
Library Manager | Bhawna Kaushik | BSD-29636 | Complete | Verified & closed | [LM2.0 DEV]: Materials are not displaying even when active filter for Upmix filter is clearing |  | Dev | Bug
Library Manager | Pedro Rodriguez | BSD-29736 | Complete | Verified & closed | LMv2 - Calculated Columns seem empty at the rendition level |  | Dev | Bug
Library Manager | Bhawna Kaushik | BSD-29738 | Complete | Verified in UAT | [LM2.0 UAT] Acts filter is not working. |  | UAT | Bug
Library Manager | Bhawna Kaushik | BSD-29739 | Complete | Verified in UAT | [LM2.0 UAT] API error is returned when user sort column Series CRID and scroll down. |  | UAT | Bug
Library Manager | Bhawna Kaushik | BSD-29751 | Complete | Verified in UAT | [LM2.0 UAT] Brand and Franchise levels are not present in Export window dropdown. |  | UAT | Bug
Library Manager | Krishna Suryavanshi | BSD-29758 | Complete | Verified in UAT | [LM2.0 UAT] Reset Filter button does not restore saved filter settings in Saved Filters. |  | UAT | Bug
Library Manager | Bhawna Kaushik | BSD-29905 | Complete | Newly created | [LM2.0 Dev] Rendition/Materials are not opening in CRMAM |  | Dev | Bug
Library Manager | Bhawna Kaushik | BSD-29928 | To Do | Newly created | [LM2.0 Dev] Changes made in saved filter are not persisting in new session even when user save those changes |  | Dev | Bug
Central Repository | Krishna Suryavanshi | BSD-29594 | Complete | Verified & closed | CR MAM Player: Playhead bar overlaps Trigger Workflow dropdown during SD playback |  | Dev | Bug
Central Repository | Bhawna Kaushik | BSD-29615 | Complete | Verified & closed | CR MAM: Season/Series/Title and Rendition "inactive" flags not respected in UI - renditions/materials remain visible |  | Dev
Central Repository | Krishna Suryavanshi | BSD-29856 | Complete | Verified & closed | Suppressed Sessions Are Also Unselectable When Viewing Segment Sessions in CR Tab View |  | Dev | Bug
Archives | Krishna Suryavanshi | BSD-29515 | Complete | Verified & closed | [Archive DEV] Additional API errors during Edit Material retest — Invalid User Interaction action and S3 MethodNotAllowed |  | Dev | Bug

## Totals
Application | Verified Dev | Verified UAT | Verified PROD | Sent to dev | Reopened | Newly created | Total
Fulfillment Console | 4 | 0 | 2 | 4 | 0 | 0 | 10
MSC Fulfillment Performance Metrics | 2 | 0 | 0 | 0 | 0 | 1 | 3
Admin Console | 2 | 0 | 0 | 0 | 0 | 3 | 5
AI Chatbot | 2 | 0 | 0 | 0 | 0 | 0 | 2
Partner Console | 2 | 3 | 0 | 2 | 1 | 6 | 14
Media Ingest Console | 2 | 0 | 4 | 5 | 0 | 5 | 16
QC Workbench | 3 | 0 | 2 | 0 | 0 | 0 | 5
Library Manager | 4 | 4 | 0 | 0 | 0 | 2 | 10
Central Repository | 3 | 0 | 0 | 0 | 0 | 0 | 3
Archives | 1 | 0 | 0 | 0 | 0 | 0 | 1
GRAND TOTAL | 25 | 7 | 8 | 11 | 1 | 17 | 69