## QA Status
Name | Jira ID | Status | QA action today | Summary | Notes | Environment | Type
Krishna Suryavanshi | ADX-5068 | Done | Verified & closed | V2-AI-MIC: Chatbot returns incorrect count for Manual QC Failed events in MIC |  | PROD | Bug
Krishna Suryavanshi | ADX-5058 | Done | Verified & closed | V2-AI-LM Chatbot (UAT) returns fewer renditions for Yellowstone 101 | LM shows 4 renditions; chatbot returned 2 | UAT | Bug
Babloo Kumar | BSD-28618 | Complete | Verified & closed | AI Chatbot: Response text font appears large and bold for ITMS failure log message |  | UAT | Bug
Babloo Kumar | BSD-29726 | Complete | Verified & closed | AI Chatbot: Duplicate response displayed in chat UI |  | UAT | Bug
Ravi Balasundaram | BSD-29725 | Complete | Verified in UAT | V2-AI-MIC: Prod ¦ Manual QC failed event Count Mismatch due to UTC Timezone Instead of IST |  | UAT | Bug
Babloo Kumar | BSD-29872 | To Do | Newly created | AI-OC-QA: Old search history prompt moves to Today section when reopened |  | UAT | Bug
Bhawna Kaushik | ADX-5143 | To Do | Newly created | V2-AI-LM: Incorrect media material count is returned by chatbot |  | PROD | Bug
Babloo Kumar | BSD-29727 | In Progress (DEV) | Sent to dev | AI-QA: Blue Dot Indicator Appears for Opened Prompts Instead of Only In-Progress Prompts | UAT retest failed — blue dot shown for completed/historical prompts | UAT | Bug
Babloo Kumar | BSD-29851 | In Progress (DEV) | Sent to dev | Fix UI rendering issue and duplicate responses in chatbot | UAT retest failed — duplicate responses and UI rendering issue persists | UAT | Bug

## Totals
Metric | Count
Verified & closed (Dev) | 4
Verified in UAT | 1
Verified in PROD | 0
Sent to dev | 2
Reopened | 0
Newly created | 2
Total rows | 9